## August MSAP
| Actions to reduce speed-related collisions | Target Date | Comment in December 2015 | Status
1 | TfL will provide funding for a 40 per cent uplift in the activities of the Metropolitan Police’s Motorcycle Tasking Team, part of the RTPC, to further clamp down on illegal and antisocial road user behaviour such as: •Speeding •Careless riding •Red light running •Uninsured and unlicensed riding; and •Traffic violations by motorcyclists and other roadusers | 2014 | Extra Officers not able to be recruited so activity levels being increased through overtime and extra shifts by non MST Officers |  | Complete
2 | TfL will continue to deliver market leading safety campaigns to reduce speeding by motorcyclists and to change their attitudes to speeding. | 2014 | Motorcycle 'Speed' campaign subject to October burst |  | Complete this year, but ongoing throughout the plan
3 | TfL will increase the reach and coverage of motorcycle speed compliance by installing rear facing cameras on the A13 to enforce the speed limit. TfL will ensure that all average speed camera trial locations will enforce the speed limit with rear facing cameras. | 2015 | A13 being upgraded to become operational |  | In progress, work started
4 | The Mayor and TfL will work with London’s police to embed the use of Speed Awareness Courses for motorcyclists as an alternative to prosecution, in cases of minor speed infractions. | 2016 | Motorcyclists are being offered SACs where they meet the criteria set out by NPCC |  | Not started
| Actions to reduce right turning vehicle collisions |  |  |  | Not started, at risk of non completion or overdue
5 | TfL will produce hard-hitting safety campaigns to change road user behaviour that currently puts motorcyclists at risk, with a particular focus on areas such as: •Drivers failing to look properly or to accuratelyjudge motorcyclists’ paths when turning into orout of side roads, U-turning without appropriatecare, changing lanes across motorcyclists’paths •Raising awareness among other road users ofthe presence and vulnerability of motorcycliststo increase the level of empathy drivers have formotorcyclists •The particular dangers that motorcycliststhemselves face when other drivers are turningright or when they are filtering | all 2015 | New 'Road User Behaviour' campaign launched in late October 2015. Risky manoeurves by motorists is included
6 | Building on the Institute of Highway Engineers’ forthcoming design guidelines for motorcycling, TfL will produce new design guidance tailored for London. Used on all TLRN schemes, this will draw on the knowledge of motorcycle safety experts to embed motorcycle safety within the design process. TfL will use the borough Local Implementation Plan process to encourage boroughs to apply these principles to their roads. | 2015 | Project commissioned and almst complete for a February 2016 completion
7 | TfL will proactively trial new technologies designed to make motorcycling safer. For example, the use of innovative lighting displays designed to increase the width of a motorcycle’s visual footprint in order to reduce right turning ‘failed to look’ collisions. | 2016 | This action has not yet commenced and is on TfL’s list of future research proposals.
Actions to increase enforcement and compliance with the rules of the road
8 | Building on the success of Operation Safeway, TfL and the police, through the new Metropolitan Police Service Roads and Transport Policing Command (RTPC), will ensure that future monthly high visibility traffic enforcement operations will target motorcycle safety alongside that of pedestrians and cyclists. | 2015 | Ongoing Operation Winchester activity
9 | TfL will work with the police to use alternative disposal schemes, such as the Rider Intervention Developing Experience, instead of issuing penalty charge notices for lower order offences. | 2015 | RIDE is now being offered to riders. Efforts continue to increase the number of courses offered
10 | TfL will fund Scootersafe-London and Bikesafe-London rider assessment days for all high risk riders who have been involved in slight injury collisions in London. | 2015 | This was trialled in 2014 with a relatively low successful conversion rate
11 | TfL will work with the police to crack down on illegal bikes and riders, as well as cars, forcing them off the road through the ongoing Operation CUBO and other targeted operations. | 2015 | Operation CUBO and other operations continune as BAU
Actions to increase the use of Personal Protective Equipment to prevent or reduce injury severity
12 | TfL will advocate and encourage, through a focused programme of engagement, the increased use of PPE by motorcyclists in order to reduce the severity of the injuries they incur when involved in a collision by: • Calling on the motorcycle industry and retailers to continue to promote and increase the availability and usage of PPE • Encouraging manufacturers to develop new types of clothing and take forward other PPE advances such as air-bag jackets and use of light weight materials • Encouraging manufacturers and dealers to broaden their ranges of PPE to include clothing for smaller bikes and younger riders • Working with boroughs where motorcyclists experience high levels of risk to implement local awareness campaigns | 2015, 2014, 2014, 2014 | Marketing campaigns and other interventions are encoroughing knowledge of and use of PPE by riders
13 | TfL and the boroughs will work with the motorcycle industry and rider groups to improve awareness among riders on choosing and wearing helmets correctly. | 2016 | This has been incorporatedwith the PPE behaviour change work
14 | The Mayor and TfL will lobby the DfT to include more makes and models of helmets in their Safety Helmet Assessment and Rating Programme so that members of the public are properly informed about helmet safety performance and that future test standards are continually improved. | 2014 | DfT have continued the SHARP programme so action no longer active
Actions to improve motorcyclist skill and riding behaviour
15 | TfL will develop and pilot a new approach involving schools, colleges, universities, trainers, retailers and businesses in order to reach out to young riders who are most at risk. | 2015 | Working with Lewisham borough to develop a pilot
16 | The Motorcycle Industry Association, working with TfL, will increase the availability of post-test training through promotions, incentives and industry shows. | 2015 | Promotions and advertising undertaken by MCIA and TfL
17 | TfL will undertake a wide ranging review of Scootersafe-London and Bikesafe-London to ensure they reflect the most up-to-date evidence and best practice in motorcycle safety. | 2014 | Course content refreshed in 2014
18 | TfL will use the latest data analytics to ensure that its campaigns are targeted and delivered to the right groups and through the right channels by: • Making better use of data from the LTDS, crime reporting and MOSAIC classifications to better inform campaign design and implementation • Increasing our knowledge of riders who live outside London but regularly ride in London • Identifying collision hotspots where there has been a disproportionately high number of injuries among BAME groups and using this data to influence future initiatives by boroughs • Making road safety materials available to London boroughs and the police to improve campaign co-ordination across London • Working with local authorities outside London to ensure that campaign, education and training materials reach those commuting into or visiting London • Using peer-to-peer engagement with hard to reach groups of young riders when needed | 2015, 2015, 2014, 2014, 2014, 2015 | Data analysis regularly undertaken and shared as part of the priority borough engagement efforts
19 | TfL, with representatives from the motorcycling industry, will launch a new motorcycle courier and delivery rider code to protect those who use a motorcycle for work and to instil better riding behaviour among their riders. | 2015 | Now to be styled as 'top tips' advice to riders stop on 'engagement operation'
Actions to deliver in partnership
20 | TfL, with partners, will undertake a multi-modal research study into younger riders and drivers to better understand their attitudes and behaviour to safety which will influence future road safety initiatives in London. | 2014 | Motorcyclist segmentation research has provded further insight into motorcyclist attitudes. Requierments for further research will be kept under review.
21 | TfL and the police will update the motorcycle fatality files research study to identify any emerging safety issues that lead to fatal collisions. | 2015 | Date to be reset to 2016 or 2017 because of issues accessing Police data
22 | TfL, in partnership with the Motorcycle Industry Association, will investigate motorcycle safety in European cities that have lower motorcycle injury rates than London and apply the lessons learned from this review. | 2014 | Behaviour change European Best Practice project completed
23 | The Road Fatality Review Group, including senior representatives from the police and TfL, will meet every two months and will use the latest ‘Compstat’ style approaches from crime analysis to improve the safety of motorcycles at high priority junctions. | 2014 | Road Fatality Review Group meetings have been held in 2014 and 2015, and the format is current being reviewed to ensure that is as effective as possible in identifying trends in motorcyclist KSIs
24 | TfL will develop and fund new engineering guidance and training to up-skill London’s road safety professionals and address the unique needs of motorcycle safety in the Capital. | 2016 | Project commissioned and almst complete for a February 2016 completion
25 | TfL will enable boroughs to target locations where motorcycle safety improvements are needed by providing, every year, information on high risk locations. | 2015 | Priority maps for motorcycle KSIs sent to boroughs
26 | The Road Safety Steering Group and Motorcycle Safety Working Group will define new areas of research and evidence by: • Bringing together hospital, trauma and police data to better understand how injuries happen and to identify ways to increase motorcyclists chances of avoiding injury in collisions • Bringing experts and leading practitioners to seminars and events to further spread motorcycle safety best practice. | 2014 | HES research study due for completion in 2015, project was delayed because of consultancy approval and data sourcing delays
27 | The Mayor and TfL will lobby the DfT for further safety and training elements to be included in the motorcycle compulsory basic training and the motorcycle licence test. | 2015 | Scoping started July 2015 and lobbying of DfT now underway
28 | TfL, working with the DfT, the Driver and Vehicle Standards Agency, industry and motorcycle user groups, will ensure that motorcycle training standards in London are industry-leading using the safest practices and equipment. | 2016 | Investigation into the CBT London market started to develop an initiative on this
29 | TfL, through the motorcycle working group, will work with the motorcycle industry in Europe to continue to develop future designs and technology to improve motorcycle safety through trials and knowledge sharing. | 2016 | Scoping meeting with MCIA being planned